## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 课程作业提醒 | 作为一个学生，我希望能够有一个课程作业提醒，以便于提醒我按时完成作业。 | Initial Feature | Not Done | 3 | 96 |  |  | 2
2 | 1 | 1 | user story | 课程表 | 作为一个学生，我希望可以有一个课程表，以便于时间管理 | Initial Feature | Not Done | 3 | 98 |  |  | 1 | #REF!
3 | 1 | 1 | user story | 直播 | 作为一个老师，我希望可以进行直播，以便于更好的线上教学。 | Initial Feature | Not Done | 3 | 99 |  |  | 3
4 | 1 | 1 | user story | 课程提醒 | 作为一个学生，我希望可以有一个课程提醒，以便于我进行预习和准备 | Initial Feature | Not Done | 1 | 93 |  |  | 1 | #REF!
5 | 1 | 1 | user story | 课程视频推荐 | 作为一个学生，我希望可以有一个课程推荐，以便于我针对性学习 | Initial Feature | Not Done | 5 | 99 |  |  | 2 | #REF!
6 | 1 | 1 | user story | 提交作业系统 | 作为一个老师，我希望有一个晚上的提交作业系统，以便于对学生课业进行管理 | Initial Feature | Not Done | 0.5 | 90 |  |  | 1 | #REF!
7 | 1 | 1 | user story | 直播回放 | 作为一个学生，我希望有一个直播回放，以便于我可以复习老师课上讲的内容 | Initial Feature | Not Done | 2 | 92 |  |  | 2 | #REF!
8 | 1 | 1 | user story | 班级分组 | 作为一个老师，我希望有一个班级分组，以便于我对学生进项管理 | Initial Feature | Not Done | 2 | 92 |  |  | 3 | #REF!
Total |  | 8 | [5 empty] | 19.5
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information
Note on C10: Luc Segers: Total amount of stories available in the project backlog
Note on I10: Luc Segers: total amount of estimated hours

## Sheet2
| TODAY: | 2020-12-17 |  |  | Ideal Curve |  | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| SPRINT NAME: | Sheet2 | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| # Days / Sprint: | #N/A | Total Baseline Hours : |  | 0 | Remaining : | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
备录编号 | 冲刺备录项 |  | 责任人 | 状态 | 预期 | 剩余 | 底线 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
| 作为一个学生，我希望能够有一个课程作业提醒，以便于提醒我按时完成作业。 | 用户课程统计 | 刘传开
|  | 作业提取 | 李炬宇
|  | 前端界面实现 | 张辰敏
| 作为一个学生，我希望可以有一个课程推荐，以便于我针对性学习 | 前端界面实现 | 张辰敏
|  | 课程视频界面 | 杨泽宇
|  | 课程视频推荐 | 王瑞康
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0